## Sheet1
Project Title: eTool Development
Partner Point of Contact: Travis Sondgerath | [26 empty] | April 1 - Septempber 30 2021
Key Project Activities | Key Partner-specific Activities (Brief) | State of implementation | [24 empty] | Results
|  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Support use and business processes around using additional Ona forms | Alter equipment information form | Added a new form to change a single characteristic of a piece of equipment. | bar: April W1 to April W4
| Submit maintenance request form | Altered how these are handled in the eTool. | bar: April W1 to April W4
| Submit calibration request form | Altered how these are handled in the eTool. | bar: April W1 to April W4
Create additional forms to allow users to correct data entry mistakes or alterations of equipment information | For example, email of the service provider or incorrectly entered equipment location | Added a new form to change a single characteristic of a piece of equipment. | bar: April W1 to April W4
Refactor code to support complete automation of eTool reported activities | • The first step is to create a pipeline script that could run daily, thinking it would be smart to export all the resulting data into the shiny-server folder to speed up the app. Plus this could consolidate the data and handle any logic. | The eTool will now run off files referenced in process created from below step. | bar: May W1 to June W4
| Automate scripts for data processing to populate the eTool to run more quickly. | Created data processing scripts so that pulling data from Ona and making necessary transformations is taken out of the eTool. This will help the eTool to run faster. | bar: May W1 to June W4
| .Automate scripts to send service providers alerts. | Next on the list. | bar: May W1 to June W4
Make aesthetic improvements to the eTool | Obtain feedback on eTool layout from the leadership Team, make suggested changes to layout and aesthetics. | Will follow-up with screen shots, notes, and asks for specific feedback. | bar: July W1 to July W4
Add branding (graphics, colors, etc) to leadership specifications. | bar: July W1 to July W4
Administrative activities | Add report viewers to eTool authentication. | bar: August W1 to August W4
Provide training and documentation as appropriate. | bar: August W1 to September W4
Create a final report of activities. | bar: September W1 to September W4