## Sheet1
Project Title: eTool Development
Partner Point of Contact: Travis Sondgerath
Key Project Activities | Key Partner-specific Activities (Brief) | State of implementation | [6 empty] | Additional Information | Results
|  |  | August |  | Sep
|  |  | W3 | W4 | W1 | W2 | W3 | W4
Support the development of Ona surveys to be used to in the field to collect data on newly deployed equipment, as well as to update data on existing equipment already in circulation | Pilot data collection forms in the field | Request out to CDC Nigeria to review data collection forms. | bar: August W3 to August W4
| Focus specifically on collecting data using the form for newly added equipment (dependent upon field collection of data) | Request out to CDC Nigeria to review data collection forms. | [7 empty] | Soliciting feedback from CDC Nigeria. | bar: August W3 to August W4
Support the deployment of an ASLM administered reporting platform | Support technical training to make code changes to existing eTool code base | Will develop documentation to explain the existing eTool code to pass on. | bar: Sep W3 to Sep W4
| Support user testing of the tool | Will request feedback on existing reports in the eTool. | bar: Sep W3 to Sep W4
| Deploy existing reports to the platform and add scheduled and contextual reminders for users to view these reports | Request out for funding for shinyapps.io account to publish reports to. | bar: Sep W2 to Sep W4
Develop a final report describing activities | Create necessary documentation to describe activities | Documenting progress on an ongoing basis.